## Project Profile
Defect Tracking Sheet
TMT/TD05/TMP
Project ID
Project Name
Prepared/Modified by | Role | Date of Preparation
Reviewed by | Role | Date of Review
Approved by | Role | Date of Approval
Circulation List
Version Number | <version no>

## Defect Tracking Sheet
Project ID: | PRJ_AddExam_001 | Project Name : Add Exam | [23 empty] | VERIFIED
CLOSED
Defect Id. | Module name | Defect Summary | Defect Description | Defect Category | Detected in Browser | Environment | Defect Severity | Defect Priority | Detected in Release # | Detected in Build # | Reported Date | Reported By | Assigned To | Status | Review type / Test Cycle | Test Case No. | Defect Count | Fixed Date | Verified Date | Verified By | Verified in Release # | Verified in Build # | Attachements | Comments |  | REOPENED | Coding |  |  | Internal Dev
DF_AE_01 | Add Exam | On clicking the 'Submit' Button without filling all mandatory fields the application is found not displaying any alert messages to fill the fields. | Defect Description: On clicking the 'Submit' Button without filling all mandatory fields the application is found not displaying any alert messages to fill the fields. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on 'login' link 4. Enter username & pasword 5. Click on 'Add Exam' link. 6. Click on 'Submit' button Actual result observed on running above steps: On excuting the above mentioned steps the application is found not displaying any alert messages to fill the mandatory fields as expected | Coding | Internet Explorer | Internal Dev | P0 | High | 1.3.6 | 6 | 2019-01-23 | J Anushri |  | ACT |  | TC_AE_03 | [8 empty] | PPR | FIXED | Design | P0 | Low | Internal QA
DF_AE_02 | Add Exam | On clicking the 'List of Exams' link the table conataining the list of exams available is found not displayed | Defect Description: On clicking the 'List of Exams' link the table conataining the list of exams available is found not displayed Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on 'login' link 4. Enter username & pasword 5. Click on 'List of Exam' link. Actual result observed on running above steps: On excuting the above mentioned steps the application is found not displaying the table conataining the list of exams available as expected | Coding | Internet Explorer | Internal Dev | P1 | High | 1.3.6 | 6 | 2019-01-23 | J Anushri |  | ACT |  | TC_AE_05 | [8 empty] | PPR | ACT | Enhancement | P1 | Medium | External Dev
DF_AE_03 | Add Exam | The "exam name" field in the form is found to accept invalid characters | Defect Description: The "exam name" field in the form is found to accept invalid characters Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on 'login' link 4. Enter username & pasword 5. Click on 'Add Exam details' link. Actual result observed on running above steps: On excuting the above mentioned steps the "exam name" field in the form is found to accept invalid characters rather than accepting only alphabets as expected. | Coding | Internet Explorer | Internal Dev | P1 | High | 1.3.6 | 6 | 2019-01-23 | J Anushri |  | ACT |  | TC_AE_06 | [8 empty] | SR | CNR | New Requirement | P2 | High | External QA
DF_AE_04 | Add Exam | The "commencement of online registration" field is found to accept past date values rather than accepting only future dates. | Defect Description: The "commencement of online registration" field is found to accept past date values rather than accepting only future dates. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on 'login' link 4. Enter username & pasword 5. Click on 'Add Exam details' link. Actual result observed on running above steps: On excuting the above mentioned steps the "commencement of online registration" field is found to accept past date values rather than accepting only future dates as expected. | Coding | Internet Explorer | Internal Dev | P1 | High | 1.3.6 | 6 | 2019-01-23 | J Anushri |  | ACT |  | TC_AE_02 | [8 empty] | QPR | NOD | Query | P3
DF_AE_05 | Add Exam | The "exam Date" Field is found to accept values that are 60 days behind the date of notice | Defect Description: The "exam Date" Field is found to accept values that are 60 days behind the date of notice Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on 'login' link 4. Enter username & pasword 5. Click on 'Add Exam details' link. Actual result observed on running above steps: On excuting the above mentioned steps the "exam Date" Field is found to accept values that are 60 days behind the date of notice rather than accepting values that are 60 days ahead of date of notice as expected. | Coding | internet Explorer | Internal Dev | P1 | High | 1.3.6 | 6 | 2019-01-23 | J Anushri |  | ACT |  | TC_AE_07 | [8 empty] | RT | REP | Documentation | Low
DF_AE_06 | Add Exam | The "Bank name" field is found not accepting more than 5 characters | Defect Description: The "Bank name" field is found not accepting more than 5 characters Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on 'login' link 4. Enter username & pasword 5. Click on 'Add Exam details' link. Actual result observed on running above steps: On excuting the above mentioned steps the "Bank name" field is found not accepting more than 5 characters. | Coding | Internet Explorer | Internal Dev | P1 | High | 1.3.6 | 6 | 2019-01-23 | J Anushri |  | ACT |  | TC_AE_08 | [8 empty] | UTC |  | Master Data | Medium
DF_AE_07 | Add Exam | On clicking the "Add Exam Details" link the application is found not navigating the admin to the add exam details form. | Defect Description: On clicking the "Add Exam Details" link the application is found not navigating the admin to the add exam details form. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on 'login' link 4. Enter username & pasword 5. Click on 'Add Exam details' link. Actual result observed on running above steps: On excuting the above mentioned steps the application is found not navigating the admin to the add exam details form as expected. | Coding | Internet Explorer | Internal Dev | P1 | High | 1.3.6 | 6 | 2019-01-23 | J Anushri |  | ACT |  | TC_AE_10 | [10 empty] | Test Review | High
Note on A3: Alphy Chenganiyadan Give a unique number for the Defect Id
Note on B3: Alphy Chenganiyadan: Give the name of the module being tested
Note on C3: Alphy Chenganiyadan: Summarize the defect in 1 or 2 lines
Note on D3: Alphy Chenganiyadan: A detailed description of the defect
Note on E3: Alphy Chenganiyadan: Categorize the defect into the one of the values given in the drop down list
Note on F3: Alphy Chenganiyadan: Mention the name of the browser the defect was found in.
Note on G3: Alphy Chenganiyadan: Mention the environment in which the defect was found.
Note on H3: P0 defect is a defect wherein the main function of the software does not work. e.g. crash, hang, data corruption P1 defect is a defect wherein a function does not work and a tedious work around exists. e.g. One of menu options does not work. P2 defect is a defect wherein the software does useful work but a degree of inconvenience is caused. Correction is not deferrable and easy work around exists. P3 defect is a tolerable defect as corrections are deferrable. E.g. cosmetic problems in user interface like spelling. “High” severity defect is a defect wherein the main function of the software does not work. e.g. crash, hang, data corruption, some of the menu functions do not work “Medium” severity defect is a defect wherein the software does useful work but a degree of inconvenience is caused. Correction is not deferrable and easy work around exists. “Low” severity defect is a tolerable defect as corrections are deferrable. E.g. cosmetic problems in user interface like spelling.
Note on I3: Prioritize the defect
Note on J3: Alphy Chenganiyadan: Enter the Release # in which the defect was detected.
Note on K3: Alphy Chenganiyadan: Enter the Build # in which the defect was detected.
Note on L3: Alphy Chenganiyadan: Mention the date the defect was reported
Note on M3: Alphy Chenganiyadan: Name of the person who reported the defect.
Note on N3: Alphy Chenganiyadan: Name of the person the defect is assigned to.
Note on O3: Alphy Chenganiyadan: Can have values: VERIFIED CLOSED FIXED ACT-Active CNR-Could Not be Reproduced NOD- Reported Bug Not a Defect REP- Repeated
Note on P3: Alphy Chenganiyadan: Values can be: PPR-Peer to Peer Review PR-Peer Review SR-Self/Programmer Review QPR-10% Quality Probe(Review) RT-Random Testing UTC-Using Test Cases
Note on Q3: Alphy Chenganiyadan: Mention the Test Case No that the defect was found while testing
Note on S3: Alphy Chenganiyadan: Mention the date the defect was Fixed
Note on T3: Alphy Chenganiyadan: Mention the date the defect was verified
Note on U3: Alphy Chenganiyadan: Name of the person who will be verifying whether the defect has got fixed after the defect has being worked upon
Note on V3: Alphy Chenganiyadan: Enter the Release # in which the defect was available for verification
Note on W3: Alphy Chenganiyadan: Enter the Build # in which the defect was available for verification
Note on X3: Alphy Chenganiyadan: Attach the proofs showing the defect-screenshots,temp files,etc
Note on Y3: Alphy Chenganiyadan: Should include all the comments on the defects till date by all touching the defect.It should be captured date wise.

## Revision History
REVISION HISTORY OF WORK PRODUCT (to be maintained by projects)
# | Date | Version # | Section Changed | Details of changes made | Approved By